## ProjectPlan
STT | TI?U ?? C?NG VI?C | NG??I PH? TR?CH C?NG VI?C | TR?NG TH?I | NG?Y B?T ??U | NG?Y ??N H?N | TH?C T? HO?N TH?NH | GHI CH?
1 | Kh?i ??ng d? ?n v? ph?m vi
1 | Ch?t scope parity so v?i demo (m?n h?nh + h?nh vi)
2 | T?o c?u tr?c 2 repo ngang c?p: starlent-web, starlent-be
3 | ??nh ngh?a vai tr?: learner/trainer/manager/editor/admin
4 | Ch?t NFR: local-first, parity h?nh vi tr??c, parity pixel sau
2 | Thi?t l?p m?i tr??ng v? ti?u chu?n ph?t tri?n
5 | Backend: t?o project FastAPI, c?u h?nh settings/env, c?u tr?c app
6 | Backend: c?u h?nh Alembic migration + chi?n l??c schema platform/tenant
7 | Frontend: t?o project React + Vite + Tailwind
8 | Frontend: c?u h?nh API client, env, x? l? l?i v? toast
9 | Thi?t l?p .gitignore, quy ??c branch/commit, coding standards
3 | Backend n?n t?ng (FastAPI + PostgreSQL + Multi-tenant)
10 | Thi?t k? schema platform: tenants/users/roles/permissions/memberships
11 | Thi?t k? schema tenant: tenant_users/courses/modules/items/content types
12 | X?y auth/login + JWT + context tenant + permission check
13 | X?y API learner/trainer/manager/editor/admin theo contract parity
14 | T?o endpoint content detail cho flashcard/video/audio/quiz/roleplay/reading
15 | B? sung tenant management API (list/detail/status/create/update/provision)
4 | Frontend n?n t?ng (React + Tailwind + Routing + Auth shell)
16 | D?ng shell layout theo role, sidebar/menu/route guard
17 | D?ng login page + x? l? session + logout
18 | T?o LoadingBlock/ErrorBlock/EmptyBlock d?ng chung
19 | D?ng khung learner dashboard, courses list/detail
20 | K?t n?i API th?t v? x? l? loading/error state
5 | Onboarding learner (3 b??c + responsive)
21 | Thi?t k? flow onboarding 3 b??c theo demo
22 | ?i?u h??ng: learner login l?n ??u -> /onboarding
23 | L?u c? local onboarding_done ?? l?n sau skip
24 | Responsive mobile onboarding theo k?ch th??c tham chi?u
6 | Learner module parity
25 | Lesson players: flashcard/video/audio/quiz/sequence/roleplay/reading
26 | Learner pages: explore/search/daily-review/offline-library/settings
27 | Learner engagement: leaderboard/chats/certificates/notifications/profile
28 | Tinh ch?nh visual parity learner theo t?ng m?n h?nh ??i chi?u
7 | Editor/Admin module parity
29 | Editor dashboard + content catalog + course builder CRUD/reorder
30 | Admin dashboard + users + courses + tenants
31 | Permission gating theo role cho to?n b? route/API
32 | Parity UI admin/editor theo d? li?u th?t
8 | Ki?m th?, smoke gate, ch?t l??ng
33 | Vi?t smoke_e2e, permission_gating_e2e, response_shape_e2e
34 | Vi?t tenant_isolation_e2e (A kh?ng th?y data c?a B v? ng??c l?i)
35 | Frontend smoke routes (SPA 200) + build check
36 | Kh?a ti?u ch? release readiness + UAT checklist
9 | Docker local stack v? seed one-time
37 | T?o Dockerfile backend/frontend + docker-compose 3 services
38 | Backend entrypoint: wait postgres -> bootstrap schema -> migrate
39 | Th?m seed_one_time: seed khi DB tr?ng, skip khi ?? c? data
40 | T?i li?u reset volume ?? reseed (docker compose down -v)
10 | CI/CD GitHub v? t?i li?u b?n giao
41 | Thi?t l?p GitHub Actions FE (build + smoke routes)
42 | Thi?t l?p GitHub Actions BE (compile + e2e scripts)
43 | Chu?n h?a README 1 ngu?n duy nh?t (CMD + Docker + seed)
44 | Chu?n b? checklist b?n giao: local run, test gate, known issues