## KeHoachDuAn
STT | TI?U ?? C?NG VI?C | NG??I PH? TR?CH C?NG VI?C | TR?NG TH?I | NG?Y B?T ??U | NG?Y ??N H?N | TH?C T? HO?N TH?NH | GHI CH?
1 | Kh?i ??ng d? ?n v? ph?m vi
1.1 | Ch?t m?c ti?u d? ?n FE/BE v? ti?u ch? ho?n th?nh
1.1.1 | X?c ??nh ph?m vi parity: h?nh vi, d? li?u, UI, responsive
1.1.2 | ??nh ngh?a out-of-scope ?? tr?nh tr?i ph?m vi
1.2 | T?o 2 repo ngang c?p: starlent-web, starlent-be
1.3 | ??nh ngh?a role nghi?p v?: learner/trainer/manager/editor/admin
2 | Thi?t l?p m?i tr??ng ph?t tri?n
2.1 | Backend: kh?i t?o FastAPI + settings/env + c?u tr?c app
2.2 | Backend: Alembic migration + schema strategy platform/tenant
2.3 | Frontend: React + Vite + Tailwind + router + api client
2.4 | Thi?t l?p .gitignore, coding standard, quy t?c branch/commit
3 | Backend n?n t?ng (FastAPI + PostgreSQL + Multi-tenant)
3.1 | Thi?t k? schema platform: tenants/users/roles/permissions/memberships
3.2 | Thi?t k? schema tenant: tenant_users/courses/modules/items/content tables
3.3 | Auth + JWT + tenant context + permission guard
3.4 | API n?n t?ng: /auth, /me, /catalog, /courses
3.5 | API role-specific: trainer/manager/editor/admin
3.6 | Tenant management API: list/detail/status/create/update/provision
4 | Frontend n?n t?ng + auth shell
4.1 | Login page + session/token + logout
4.2 | Role layout + menu + route guard
4.3 | UI states d?ng chung: Loading/Error/Empty + Toast
4.4 | K?t n?i API th?t v? x? l? loading/error
5 | Editor module parity (?u ti?n tr??c Learner)
5.1 | Editor dashboard
5.2 | Editor content catalog
5.3 | Editor course builder CRUD
5.3.1 | T?o course/module/item
5.3.2 | S?a/X?a/Reorder module/item
5.4 | Permission checks cho editor routes/API
6 | Admin module parity (?u ti?n tr??c Learner)
6.1 | Admin dashboard
6.2 | Admin users: list/create + login verify user m?i
6.3 | Admin courses
6.4 | Admin tenants + status/provision controls
6.5 | Permission checks cho admin routes/API
7 | Learner module parity
7.1 | Onboarding 3 b??c + responsive
7.2 | Learner dashboard
7.3 | Courses list + detail
7.4 | Lesson players: flashcard/video/audio/quiz/sequence/roleplay/reading
7.5 | Assignment/Survey/Live Session
7.6 | Engagement: leaderboard/chats/certificates/notifications/profile/settings
7.7 | Visual parity learner theo ?nh ??i chi?u
8 | Ki?m th? v? ch?t l??ng
8.1 | Backend smoke_e2e
8.2 | permission_gating_e2e
8.3 | response_shape_e2e
8.4 | tenant_isolation_e2e
8.5 | Frontend build + smoke:routes
8.6 | UAT checklist theo m?n h?nh v? role
9 | Docker local stack + seed one-time
9.1 | Dockerfile backend/frontend + docker-compose
9.2 | Entrypoint: wait postgres -> bootstrap schema -> migrate
9.3 | Auto-seed one-time khi DB tr?ng, skip khi ?? c? data
9.4 | Doc reset volume ?? reseed
10 | Deploy DigitalOcean + CI/CD
10.1 | Thi?t k? m?i tr??ng dev/uat/prod tr?n DigitalOcean
10.1.1 | Ch?n h? t?ng: Droplet/App Platform/Managed DB
10.1.2 | Thi?t l?p network/firewall/domain/SSL
10.2 | Chu?n b? deploy backend
10.2.1 | Env secrets theo m?i tr??ng
10.2.2 | Migration strategy khi deploy
10.2.3 | Healthcheck + process manager + log rotation
10.3 | Chu?n b? deploy frontend
10.3.1 | Build artifact + static hosting/reverse proxy
10.3.2 | C?u h?nh API base URL theo m?i tr??ng
10.4 | GitHub Actions CI
10.4.1 | FE: build + smoke routes
10.4.2 | BE: compile + e2e gates
10.5 | GitHub Actions CD
10.5.1 | Deploy dev t? ??ng khi merge nh?nh develop
10.5.2 | Deploy uat theo manual approval
10.5.3 | Deploy prod theo release tag + approval
10.6 | Post-deploy checks
10.6.1 | Smoke API/FE sau deploy
10.6.2 | Rollback checklist